## Submittal Log
Submittal Log — rc23
Submittal # | Spec Section | Spec Title | Type | Description | Manufacturer | Product | Status | Responsible Party | Due Date | Submitted Date | Approved Date | Rev | Notes
rc23-001 | 00 72 13 | GENERAL CONDITIONS | certificates | Affidavit required under Quality Assurance Article. |  |  | draft |  |  |  |  | 0
rc23-011 | 00 72 13 | GENERAL CONDITIONS | closeout | Waste Shipment Records and Disposal Site Receipts: Copy of waste shipment record and disposal site receipt showing that the ACM has been properly disposed. |  |  | draft |  |  |  |  | 0
rc23-012 | 00 72 13 | GENERAL CONDITIONS | closeout | Daily Log - Submit copy of the daily air sample analytical reports and a copy of Asbestos Abatement Contractor’s Daily project log. |  |  | draft |  |  |  |  | 0
rc23-013 | 00 72 13 | GENERAL CONDITIONS | closeout | Personal Air Monitoring Data - Submit copy of personal air monitoring analytical reports and chain of custody. |  |  | draft |  |  |  |  | 0
rc23-014 | 00 72 13 | GENERAL CONDITIONS | product_data | Catalog sheets, specifications and installation instructions for each item specified. |  |  | draft |  |  |  |  | 0
rc23-015 | 00 72 13 | GENERAL CONDITIONS | product_data | Manufacturer’s installation instructions shall be provided along with product data. |  |  | draft |  |  |  |  | 0
rc23-016 | 00 72 13 | GENERAL CONDITIONS | product_data | Form systems and ties. |  |  | draft |  |  |  |  | 0
rc23-017 | 00 72 13 | GENERAL CONDITIONS | product_data | Mix Design. |  |  | draft |  |  |  |  | 0
rc23-018 | 00 72 13 | GENERAL CONDITIONS | shop_drawings | Placing drawings for bar reinforcement. |  |  | draft |  |  |  |  | 0
rc23-019 | 01 10 00 | SUMMARY OF THE WORK | other | Cameras (except with written permission from the Director’s Representative). F. Comply with Facility policies relating to smoking at the Site. G. Routes of ingress and egress within the building to the location of the Work shall be as directed by the Director’s Representative. H. Store materials and perform the Work so that pedestrian and vehicular traffic is not obstructed. I. Do not diminish the. |  |  | draft |  |  |  |  | 0
rc23-020 | 01 10 00 | SUMMARY OF THE WORK | other | Submittal — SDS tab is organized by prime contracts. To be readily identified, name products with SDS by specification section number and product name. |  |  | draft |  |  |  |  | 0
rc23-022 | 01 10 00 | SUMMARY OF THE WORK | other | Submittal — Supply and maintain one hard copy of the appropriate SDS on the project site and one hard copy with the Facility’s Right-to-Know Information Officer. |  |  | draft |  |  |  |  | 0
rc23-023 | 01 10 00 | SUMMARY OF THE WORK | other | Submittal — Supply and maintain one hard copy of the appropriate SDS on the project site and one hard copy with the Facility’s Right-to-Know Information Officer. |  |  | draft |  |  |  |  | 0
rc23-024 | 01 10 00 | SUMMARY OF THE WORK | other | Supply and maintain one hard copy of the appropriate SDS on the project site and one hard copy with the Facility’s Right-to-Know Information Officer. O. Direct employees to be watchful for people in or near the work area where safety hazards may be present. Notify the Facility Safety/Security Department, if necessary, to remove them from the work area or Site. P. Report fire and other emergency si. |  |  | draft |  |  |  |  | 0
rc23-025 | 01 10 00 | SUMMARY OF THE WORK | other | Submittal — If related contractors fail to furnish drawings or written information covering the openings and chases they require in new construction at least 24 hours before installation of the Work affected by those items, the related contractors will be required to do all cutting, patching, and refinishing of the construction so affected, at their own expense. |  |  | draft |  |  |  |  | 0
rc23-007 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — Complete Scope of work. |  |  | draft |  |  |  |  | 0
rc23-021 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — Confined Space entry program and procedures for entry, when applicable. |  |  | draft |  |  |  |  | 0
rc23-026 | 01 11 00 | SAFETY | other | SITE SPECIFIC SAFETY PLAN including cover page, complete scope of work, roles and responsibilities, PPE program, work attire program, fall protection program, safety talks program, confined space entry program, respirable silica protection plan, hazard identification, high hazard assessments, safety inspection program, injured employee care program, emergency action and evacuation plan. |  |  | draft |  |  |  |  | 0
rc23-027 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — Cover page including Project Name/Location/Project Number/Contractor Name/Potential Start/Finish Dates. |  |  | draft |  |  |  |  | 0
rc23-028 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — Roles and Responsibilities page identifying Supervision, list of the names of all competent and/or qualified persons, including their qualifications, for each activity requiring a competent person i.e. excavations, scaffolding, rigging, fall protection, etc. |  |  | draft |  |  |  |  | 0
rc23-029 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A program for implementing appropriate PPE as specified in the High 5. Hazard Assessment detailed in Subparagraph 1.04 A.11 below. |  |  | draft |  |  |  |  | 0
rc23-030 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A program for assuring employees have proper work attire, i.e. substantial sole safety-toed footwear, long pants, shirts with minimum 4- inch sleeves, etc. Updated 12/14/2021 Printed 12/17/2025 011100 - 1 Project Nos. 47444 – C, E, H, P |  |  | draft |  |  |  |  | 0
rc23-031 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A 100% 6-foot conventional fall protection program which provides full body harnesses, lanyards (connectors), and anchorage points, or guardrails for all trades when working 6 feet above a lower level. a. Exception: 1) When the employer can demonstrate that it is infeasible or creates a greater hazard to utilize these systems, the employer shall develop and implement a Fall Protection Plan, which meets the requirements of paragraph (k) 1926.502. This plan must be approved before implementation by the applicable OGS Regional Safety Manager. 2) When working from portable ladders. |  |  | draft |  |  |  |  | 0
rc23-032 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A program for raising employee awareness through the use of weekly Safety Talks (i.e. “Toolbox Talks” or “Tailgate Meetings”) on topics related to upcoming/relevant work on the project. Contractor shall be required to verify that all employees on site participated in meeting, with documentation submitted to the Director’s Representative. |  |  | draft |  |  |  |  | 0
rc23-033 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A written Respirable Silica Protection Plan, including tasks for which employees could reasonably be expected to be exposed to harmful silica dust, and control methods that will be used to limit or eliminate exposure, as well as any PPE necessary to ensure protection. |  |  | draft |  |  |  |  | 0
rc23-034 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — Identify specific hazards related to this Project, and how employees will be protected from those hazards. |  |  | draft |  |  |  |  | 0
rc23-035 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — High Hazard Assessment’s detailing procedures for all high hazard work activities including, but not limited to: a. All lifts involving cranes or material handling equipment. b. Scaffolding where scaffold working deck is expected to be 10’ or higher from a lower level. c. Demolition. d. Excavations where anticipated depth is 5’ or more. e. Hot work activities, which shall follow all applicable requirements stated in NFPA 51B. f. Steel erection with specific fall protection requirements detailed. g. Work at elevations, including roofing work. h. Electrical work involving Lock Out - Tag Out (LOTO) procedures. 1) High Hazard Assessments shall include a step-by-step breakdown of a given task, the hazards associated with each step, the controls that will be utilized to eliminate or minimize the hazards, and the PPE that will be used to protect from remaining hazards. 2) All required certifications shall be provided for all applicable types of work with required training/certifications (i.e. Powder Actuated Tools, Aerial Lifts, Forklifts, Crane Operators License, etc.). |  |  | draft |  |  |  |  | 0
rc23-036 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A project safety inspection program, with a minimum of one documented safety inspection per week, during the course of construction. Submit copies of all resultant inspection reports to the Director’s Representative on a weekly basis. Updated 12/14/2021 Printed 12/17/2025 011100 - 2 Project Nos. 47444 – C, E, H, P |  |  | draft |  |  |  |  | 0
rc23-037 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — A program for providing proper care for injured employees, including the name of the employee with First Aid/CPR certification who will be on site at all times during the course of construction, to include local hospital/medical facility locations and contact information. |  |  | draft |  |  |  |  | 0
rc23-040 | 01 11 00 | SAFETY | other | A SITE SPECIFIC SAFETY PLAN no later tha — Provide an Emergency Action and Evacuation Plan, including Fire Protection and Emergency Response, when applicable. a. Plan to include: 1) Procedures for reporting a fire or other emergency. 2) Procedures for emergency evacuation, including type of evacuation and exit route assignments. 3) Emergency Contact information. 4) Procedures on how to alert workers of an emergency. 5) Procedures to account for all employees after evacuation and muster/evacuation points. 6) A list of all major fire hazards, to include type of fire protection equipment necessary to control hazard. |  |  | draft |  |  |  |  | 0
rc23-041 | 01 11 00 | SAFETY | other | Safety orientation training for each employee prior to their starting work on site. This orientation shall include, but not be limited to: Fitness for Duty (drug, alcohol, and cannabis policies), training on general safety hazards, site- specific safety policies and procedures, personal protective equipment, injury reporting and protocols, emergency evacuation and preferred medical provide. |  |  | draft |  |  |  |  | 0
rc23-042 | 01 22 00 | COST COMPUTATIONS | other | Agreed to Amount — ACTUAL COSTS - By determining the actual cost of the extra work in the same manner as in the above Subparagraph 1.01 A. 1.a. except that actual costs of the Contractor be utilized in lieu of estimated costs. The State shall have the option to utilize this method provided it notifies the Contractor of its intent to do so prior to the time the Contractor is properly authorized to commence performance of such work. |  |  | draft |  |  |  |  | 0
rc23-043 | 01 22 00 | COST COMPUTATIONS | other | Agreed to Amount — By applying the applicable price or prices set forth in the Contract Documents or by applying a unit price agreed to by both parties. |  |  | draft |  |  |  |  | 0
rc23-045 | 01 22 00 | COST COMPUTATIONS | other | Agreed to Amount — All profit, overhead and expense of whatsoever kind and nature, other than those set forth above in Subparagraphs A.1.a. 1), 2) and 4), and below in Paragraph 1.01 F., of the Contractor, its subcontractors and sub-subcontractors, are covered by the aforesaid percentage overrides and no additional payment therefore will be made by the State. |  |  | draft |  |  |  |  | 0
rc23-046 | 01 22 00 | COST COMPUTATIONS | other | All profit, overhead and expense of whatsoever kind and nature, other than those set forth above in Subparagraphs A.1.a. 1), 2) and 4), and below in Paragraph 1.01 F., of the Contractor, its subcontractors and sub-subcontractors, are covered by the aforesaid percentage overrides and no additional payment therefore will be made by the State. B. Irrespective of the method used or to be used by the S. |  |  | draft |  |  |  |  | 0
rc23-047 | 01 22 00 | COST COMPUTATIONS | other | Submittal — Travel costs including mileage, tolls, and overnight lodging and meal per diems incurred as a result of the extra work will be reimbursed at costs without any markup for the Contractor or subcontractor as the case may be. Daily travel to the project site must exceed 35 miles, one way, from the Contractor’s office address to claim mileage and toll expenses; only mileage beyond 35 miles will be reimbursed. Distance must exceed 50 miles, one way, from Contractor’s office address to the project site to claim overnight lodging and meal per diems. Actual cost for overnight lodging and meal per diems will be reimbursed up to the maximum rates listed per locality, as established by U.S. General Services Administration (GSA). |  |  | draft |  |  |  |  | 0
rc23-048 | 01 22 00 | COST COMPUTATIONS | other | Submittal — Personal Protection equipment required for hazardous materials abatement and materials used to create critical barriers and protection barriers, provided that they are expended during the performance of the extra work or turned over to the State at the request of the Director’s Representative, are reimbursable as part of an order on contract. |  |  | draft |  |  |  |  | 0
rc23-050 | 01 30 00 | ADMINISTRATIVE REQUIREMENTS | other | CONTRACTOR’S LIST OF SUBCONTRACTORS – SUPPLIERS: An affirmative review of the subcontractor’s responsibility will be conducted. Any subcontractor disapprovals resulting from negative information derived from the State’s review will result in written notice (by letter or e-mail) to the Contractor. A responsibility meeting may result from these actions. The Contractor will defer to the provisions of. |  |  | draft |  |  |  |  | 0
rc23-051 | 01 30 00 | ADMINISTRATIVE REQUIREMENTS | other | The DETAILED ESTIMATE information using the required electronic entry process via the Vendor Interface. B. The detailed estimate shall be supported by such evidence, including certified copies of subcontracts, as the Director may require. C. The detailed estimate must be approved by the Director who may revise it as, in his reasonable judgment, is necessary to make the various items conform. |  |  | draft |  |  |  |  | 0
rc23-052 | 01 31 13 | PROJECT PLANNING AND SCHEDULING | other | No duration in any baseline or recovery schedule shall be longer than one (1) reporting period as defined in Section 013119, except for submittal items. | OGS through, OGS Scheduling as requested |  | draft |  |  |  |  | 0
rc23-053 | 01 31 13 | PROJECT PLANNING AND SCHEDULING | other | Constraints are used by OGS Scheduling in specific instances during the baseline process to hold dates dictated by the terms of the Contract or assigned to submittal & procurement items in the Project Work Plan. | OGS through, OGS Scheduling as requested |  | draft |  |  |  |  | 0
rc23-054 | 01 31 19 | PROJECT MEETINGS | other | Pre-installation meetings will be held to review the specifications, Project Schedule, drawings, and approved submittals in preparation for start of a particular activity. |  |  | draft |  |  |  |  | 0
rc23-044 | 01 33 00 | SUBMITTALS | certificates | Submittal Coordinator Qualifications: Not later than 10 days after Award. Include resume and references, and other certification, licenses, or other requested information. Revised 01/04/2024 Edited and/or Printed 12/17/2025 013300 - 3 Project Nos. 47444 – C, E, H, P. |  |  | draft |  |  |  |  | 0
rc23-056 | 01 33 00 | SUBMITTALS | other | Schedule of Submittals acknowledgement: Provide written acknowledgement that the Schedule of Submittals has been received and reviewed with Critical Submittals identified and Contractor’s Projected Dates (three dates inserted into each column) are entered for each specification item. |  |  | draft |  |  |  |  | 0
rc23-057 | 01 41 00 | REGULATORY REQUIREMENTS | other | Locate existing underground utilities prior to commencing excavation work. Conform to all requirements of NYCRR 16 Part 753, including the following: a. Notify UDig NY at least 48 hours in advance, not counting the date of contact. 1) Statewide: Phone Number: 811. 2) Website: https://udigny.org/ b. Refer to Project Manual Section 023313 “Underground Utility Locator Service” to locate all utilities. |  |  | draft |  |  |  |  | 0
rc23-055 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — Receptacle outlets, portable cord connectors and attachment plugs shall have standard NEMA configurations. |  |  | draft |  |  |  |  | 0
rc23-058 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Any Contractor who requires additions to the construction facilities and temporary controls specified to be provided by another Contractor, shall provide and maintain them. |  |  | draft |  |  |  |  | 0
rc23-059 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — Install materials for temporary light and power in conformance with the National Electrical Code. |  |  | draft |  |  |  |  | 0
rc23-060 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — Materials for temporary light and power need not be new if they are in satisfactory operating condition. |  |  | draft |  |  |  |  | 0
rc23-061 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — Provide ground-fault protection for personnel (such as portable plug-in type ground-fault circuit-interrupters) on single phase 15 and 20 ampere receptacle outlets which are in use. |  |  | draft |  |  |  |  | 0
rc23-063 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — As the progress of the Work allows, and as approved, completed portions of the permanent wiring and electrical service may be utilized for temporary light and power. Updated 03/17/2016 Printed 12/17/2025 015000 - 1 Project Nos. 47444 – C, E, H, P |  |  | draft |  |  |  |  | 0
rc23-064 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — Inside buildings, locate toilet facilities no more than 4 stories or 60 feet above or below, nor more than 500 feet travel on the same level from the work location of any person. |  |  | draft |  |  |  |  | 0
rc23-065 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Submittal — Locate toilet facilities no more than 1000 feet from any work location. a. Exception: Mobile crews having readily available transportation to nearby toilet facilities. |  |  | draft |  |  |  |  | 0
rc23-066 | 01 50 00 | CONSTRUCTION FACILITIES & TEMPORARY CONTROLS | other | Locate toilet facilities no more than 1000 feet from any work location. a. Exception: Mobile crews having readily available transportation to nearby toilet facilities. B. Construction Work Contract: Provide the following toilet facilities for use by the general public. Locate toilets where directed, and maintain them in a sanitary condition. Provide and maintain paper, soap, and water supplies:. |  |  | draft |  |  |  |  | 0
rc23-062 | 01 71 23 | FIELD ENGINEERING | other | On request, submit documentation verifying accuracy of survey work. |  |  | draft |  |  |  |  | 0
rc23-067 | 01 71 23 | FIELD ENGINEERING | certificates | Upon completion of the Work, submit a certificate signed and sealed by the Land Surveyor, stating that the elevations and locations of the Work are in conformance with the Contract Documents. |  |  | draft |  |  |  |  | 0
rc23-068 | 01 71 23 | FIELD ENGINEERING | other | The name, address, telephone number, and registration number of the Land Surveyor before starting the survey work. |  |  | draft |  |  |  |  | 0
rc23-069 | 01 77 16 | CONTRACT CLOSEOUT | closeout | Label the CD with the project number, name, and title as it appears on the project manual cover. If there is more than one CD include notation to that effect on the label; i.e., 1 of 3, 2 of 3, 3 of 3. The project record documents and CD(s) are to be turned over to the Director’s Representative. F. Applications for progress payments will not be approved if the record documents are not kept current. |  |  | draft |  |  |  |  | 0
rc23-070 | 01 77 16 | CONTRACT CLOSEOUT | product_data | Reviewed shop drawings, product data, and samples. B. Store record documents separate from documents used for construction. C. Record information concurrent with construction progress. D. Record Documents and Shop Drawings: Legibly mark each item to record actual construction including:. |  |  | draft |  |  |  |  | 0
rc23-038 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Quality Control Submittals — Submit Quality Control Submittals within 10 days of contract award. |  |  | draft |  |  |  |  | 0
rc23-071 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Detailed experience and qualification information about the underground utility locator service company and the persons performing the Work, including project information of 5 similar projects. |  |  | draft |  |  |  |  | 0
rc23-072 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Description of types of utility locator equipment that company will utilize to perform the underground utility investigation. |  |  | draft |  |  |  |  | 0
rc23-073 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Names of persons performing the Work, including years of experience and training, and copy of training certificates for locator equipment. |  |  | draft |  |  |  |  | 0
rc23-074 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Detailed written report and scaled drawings of the subsurface investigation. |  |  | draft |  |  |  |  | 0
rc23-075 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Quality Control Submittals — Submit detailed experience and qualification information about the underground utility locator service company and the persons that will be performing the Work. Detailed experience and qualification information shall include: a. Minimum of five (5) years experience in field locating, marking and staking out of existing underground utilities and service connections. 1) Qualifying Experience: Project information of 5 similar projects, which the locator service company, had worked on during the past 5 years. Information shall include for each project: a) Name and Address of project. b) Dates worked on project. c) Name and telephone Number of contact person at the project site for which the locator service was performed. b. Description of types of utility locator equipment (investigation equipment) that company will utilize to perform the underground utility investigation. Updated 06/01/2024 Printed 12/17/2025 023313 - 2 Project No. 47444 – C c. Names of persons that the persons that will be performing the Work, including the number of years of experience and training that the persons have in the use of the equipment. Include copy of training certificates for locator equipment proving the person performing the locator service are trained on the equipment being used. |  |  | draft |  |  |  |  | 0
rc23-076 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Investigative Report — Submit detailed written report and scaled drawings of the subsurface investigation, documenting all underground utilities and service connections located and identified. a. All documentation shall be referenced to existing data (horizontal and vertical) previously established. b. Provide three (3) paper copies and one (1) electronic copy of detailed written report and drawings. |  |  | draft |  |  |  |  | 0
rc23-077 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | Investigative Report — Submit Investigative Report at least two weeks prior to advancing construction within the scheduled areas of excavation within the project site. |  |  | draft |  |  |  |  | 0
rc23-078 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Detailed list of the codes, rules and regulations which are understood to govern the Work, citing specific title, chapter, and section. |  |  | draft |  |  |  |  | 0
rc23-079 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Listing of licenses or permits issued by government agencies authorizing the handling of the waste by the qualified Company, transporter, and operator of the disposal facility. |  |  | draft |  |  |  |  | 0
rc23-080 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Detailed step by step procedure indicating how the Work is to be accomplished, including method of disposal, owner and operator of the disposal facility, location of the disposal facility, and method of transporting to the disposal facility. |  |  | draft |  |  |  |  | 0
rc23-081 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Qualified Company Data including name, address, telephone number, brochure explaining services offered, experience applicable to the required services, and type and listing of equipment proposed to be used for the Work. |  |  | draft |  |  |  |  | 0
rc23-082 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Quality Control Submittals — Detailed list of the codes, rules and regulations which are understood to govern the Work. This list must cite specific title, chapter, and section of the citation. |  |  | draft |  |  |  |  | 0
rc23-083 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Quality Control Submittals — Listing of licenses or permits issued by government agencies authorizing the handling of the waste by the qualified Company, transporter, and operator of the disposal facility. |  |  | draft |  |  |  |  | 0
rc23-084 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Quality Control Submittals — Detailed step by step procedure indicating how the Work is to be accomplished. Procedure shall also include information for off-site Work, such as: a. Method of disposal. b. Owner and operator of the disposal facility. c. Location of the disposal facility. d. Method of transporting to the disposal facility. |  |  | draft |  |  |  |  | 0
rc23-085 | 02 80 03 | DISPOSAL OF NON-HAZARDOUS INDUSTRIAL-COMMERCIAL WASTE | other | Quality Control Submittals — Qualified Company Data: a. Name, address, and telephone number. b. Brochure explaining services offered. c. Experience directly applicable to the required services. d. Type and listing of equipment proposed to be used for the Work. |  |  | draft |  |  |  |  | 0
rc23-049 | 02 82 13 | ASBESTOS ABATEMENT | product_data | Product Data: Catalog sheets, specifications and installation instructions for each item specified. |  |  | draft |  |  |  |  | 0
rc23-086 | 02 82 13 | ASBESTOS ABATEMENT | other | Submittals for this section are subject to the re-evaluation fee identified in Article 4 of the General Conditions. |  |  | draft |  |  |  |  | 0
rc23-087 | 02 82 13 | ASBESTOS ABATEMENT | other | Submittals shall be provided individually in the order in which they are specified and tabbed. |  |  | draft |  |  |  |  | 0
rc23-088 | 02 82 13 | ASBESTOS ABATEMENT | other | Asbestos Site Specific Variance Submitta — One copy of the completed DOSH-751 and DOSH-465 forms. |  |  | draft |  |  |  |  | 0
rc23-089 | 02 82 13 | ASBESTOS ABATEMENT | other | Asbestos Site Specific Variance Submitta — One copy of the New York State Department of Labor site specific variance decision. |  |  | draft |  |  |  |  | 0
rc23-090 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — Notification Compliance Data: Within 2 days after notification is sent to the regulatory agencies submit one copy of each notice sent to each regulatory agency (USEPA and DOL). |  |  | draft |  |  |  |  | 0
rc23-091 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — Asbestos Removal Company Data: Name and address of proposed asbestos removal company and abatement contractor license issued by DOL. Updated 6/1/2024 Printed 12/17/2025 028213 - 3 Project No. 47444-C |  |  | draft |  |  |  |  | 0
rc23-092 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — Asbestos Worker Certification Data: Name and address of proposed asbestos abatement workers and licenses issued by DOL. |  |  | draft |  |  |  |  | 0
rc23-093 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — Work Plan: Submit one copy of the work plan required under Quality Assurance Article 1.08 (C). |  |  | draft |  |  |  |  | 0
rc23-094 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — Waste Transporter Permit: One copy of transporter’s current waste transporter permit from NYS DEC (NYS Part 364 Permit). |  |  | draft |  |  |  |  | 0
rc23-095 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — NYS Part 360 Landfill Permit: Copy of NYS Part 360 permit of landfill to be used for ACM disposal shall be licensed to receive asbestos waste by NYS DEC (NYS Part 360 Permit) and by USEPA. Out of state landfills shall provide licenses from local agencies having jurisdiction. |  |  | draft |  |  |  |  | 0
rc23-096 | 02 82 13 | ASBESTOS ABATEMENT | other | Quality Control Submittals — Negative Air Pressure Equipment: Copy of manufacturer’s and performance data of all units and HEPA filters used. |  |  | draft |  |  |  |  | 0
rc23-097 | 02 82 13 | ASBESTOS ABATEMENT | product_data | Manufacturer’s installation instructions shall be provided along with product data. |  |  | draft |  |  |  |  | 0
rc23-098 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | closeout | Contract Closeout Submittals — Assessment Report compiled by a testing lab certifying that the work area has lead concentrations below the levels specified under the cleaning criteria. |  |  | draft |  |  |  |  | 0
rc23-099 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | closeout | Contract Closeout Submittals — Disposal Site Receipts: Copy of waste shipment record and disposal site receipt showing that the lead-containing materials have been properly disposed. |  |  | draft |  |  |  |  | 0
rc23-100 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | manuals | Operation and Maintenance Data — Provide an affidavit stating that the HEPA filters to be used for this project are new and unused. |  |  | draft |  |  |  |  | 0
rc23-101 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | other | Submittals for this section are subject to the re-evaluation fee identified in Article 4 of the General Conditions. |  |  | draft |  |  |  |  | 0
rc23-102 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | other | Submittals shall be provided individually in the order in which they are specified and tabbed. |  |  | draft |  |  |  |  | 0
rc23-103 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | other | Quality Control Submittals — Worker’ Qualifications: The persons removing lead containing/coated material and their Supervisors shall be personally experienced in this type of work and shall have been employed by a company with a minimum of one year experience in this type of work. Submit a copy of documentation of completion of the EPA lead renovators training program. a. Name of lead supervisor on site during the work. |  |  | draft |  |  |  |  | 0
rc23-104 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | other | Quality Control Submittals — Detailed Work Plan: Submit one copy of the work plan required under Quality Assurance Article. |  |  | draft |  |  |  |  | 0
rc23-105 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | other | Quality Control Submittals — Waste Transporter Permit: One copy of transporter’s current NYS DEC waste transporter permit. |  |  | draft |  |  |  |  | 0
rc23-106 | 02 83 04 | HANDLING OF LEAD CONTAINING MATERIALS | product_data | Manufacturer’s installation instructions shall be provided along with product data. |  |  | draft |  |  |  |  | 0
rc23-107 | 03 11 00 | CONCRETE FORMWORK | product_data | Manufacturer’s catalog sheets, specifications, and installation/application instructions for form systems and ties. |  |  | draft |  |  |  |  | 0
rc23-108 | 03 21 00 | STEEL CONCRETE REINFORCEMENT | certificates | Quality Control Submittals — Certificates: Affidavit required under Quality Assurance Article. |  |  | draft |  |  |  |  | 0
rc23-109 | 03 21 00 | STEEL CONCRETE REINFORCEMENT | other | Submittal — Manufacturer-provided EPDs must be Product Specific Type III (Third- Party Reviewed), in adherence with ISO 14025 Environmental labels and declarations, ISO 14044 Environmental management – Life cycle assessment, and ISO 21930 Core rules for environmental product declarations of construction products and services. |  |  | draft |  |  |  |  | 0
rc23-110 | 03 21 00 | STEEL CONCRETE REINFORCEMENT | samples | Samples — Bar Supports: Full size. |  |  | draft |  |  |  |  | 0
rc23-111 | 03 21 00 | STEEL CONCRETE REINFORCEMENT | shop_drawings | Shop Drawings: Placing drawings for bar reinforcement. |  |  | draft |  |  |  |  | 0
rc23-112 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Submittal — Manufacturer-provided EPDs must be Product Specific Type III (Third- Party Reviewed), in adherence with ISO 14025 Environmental labels and declarations, ISO 14044 Environmental management – Life cycle assessment, and ISO 21930 Core rules for environmental product declarations of construction products and services. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-114 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Quality Control Submittals — Batching Plant Records: At the end of each day of placing concrete, furnish the Director’s Representative with a legible copy of all batch records for the concrete placed. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-115 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Quality Control Submittals — Concrete Pumping Equipment Data: Include manufacturer’s name and model of principal components, type of pump, and type and diameter of pipe/hose. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-116 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Submittals Package: Submit product data for design mix(es) and materials for concrete specified below at the same time as a package. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-117 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Mix Design: Submit proposed concrete design mix(es) together with name and location of batching plant at least 28 days prior to the start of concrete work. a. Include test results of proposed concrete proportions based on previous field experience or laboratory trial batches in accordance with ACI 301, Section 4. b. Pumped Concrete: Include test results of proposed design mix(es) tested under actual field conditions with the maximum horizontal run and vertical lift required for this project. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-118 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Portland Cement: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-119 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Fly Ash: Name and location of source, and DOT test numbers. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-120 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Air-entraining Admixture: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-121 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Water-reducing Admixture: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-122 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — High Range Water-reducing Admixture (Superplasticizer): Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-123 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Corrosion Inhibitor Admixture: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-124 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Accelerating Admixture: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-125 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Aggregates: Name and location of source, and DOT test numbers. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-126 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Lightweight Coarse Aggregates: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-127 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Chemical Hardener (Dustproofing): Brand and manufacturer’s name, and application instructions. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-128 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Chemical Curing and Anti-Spalling Compound: Brand and manufacturer’s name, and application instructions. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-129 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Bonding Agent (Adhesive): Brand and manufacturer’s name, and preparation and application instructions. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-130 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Expansion Joint Fillers: Brand and manufacturer’s name. | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-131 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product Data — Waterstop: Brand and manufacturer’s name, and installation instructions. Updated 06/29/2023 Printed 12/17/2025 033000 - 2 Project No. 47444 – C | The Euclid Chemical Co, W.R. Meadows, Inc, L & M Construction Chemicals, Inc, Anti Hydro International, Kaufman Products, Kaufman Products, Inc, Sika Corporation |  | draft |  |  |  |  | 0
rc23-132 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Product Data — Portland Cement: Brand and manufacturer's name. |  |  | draft |  |  |  |  | 0
rc23-133 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Product Data — Masonry Cement: Brand and manufacturer's name. |  |  | draft |  |  |  |  | 0
rc23-134 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Product Data — Lime: Brand and manufacturer's name. |  |  | draft |  |  |  |  | 0
rc23-135 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Product Data — Sand(s): Location of pit, name of owner, and previous test data. |  |  | draft |  |  |  |  | 0
rc23-136 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Portland Cement: Brand and manufacturer's name. |  | Portland Cement | draft |  |  |  |  | 0
rc23-137 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Lime: Brand and manufacturer's name. |  | Lime | draft |  |  |  |  | 0
rc23-138 | 04 05 13 | MORTAR AND MASONRY GROUT | product_data | Sand(s): Location of pit, name of owner, and previous test data. |  | Sand | draft |  |  |  |  | 0
rc23-113 | 04 22 00 | CONCRETE UNIT MASONRY | product_data | Product Data — Bar reinforcement. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-139 | 04 22 00 | CONCRETE UNIT MASONRY | certificates | Quality Control Submittals — Certificates: Affidavit required under Quality Assurance Article. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-140 | 04 22 00 | CONCRETE UNIT MASONRY | product_data | Product Data — Masonry wall reinforcement. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-141 | 04 22 00 | CONCRETE UNIT MASONRY | product_data | Product Data — Tiebars. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-142 | 04 22 00 | CONCRETE UNIT MASONRY | product_data | Product Data — Buck anchors. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-143 | 04 22 00 | CONCRETE UNIT MASONRY | shop_drawings | Shop Drawings — Submit shop drawings for precast concrete lintels. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-144 | 04 22 00 | CONCRETE UNIT MASONRY | shop_drawings | Shop Drawings — Submit placing drawings for bar reinforcement. | Heckmann Building Products, Inc, Hohman & Barnard Inc, Dur-O-Wal Inc |  | draft |  |  |  |  | 0
rc23-145 | 04 23 00 | GLASS MASONRY UNITS | product_data | Catalog sheets, specifications, and installation instructions for glass blocks and accessories specified. |  |  | draft |  |  |  |  | 0
rc23-146 | 04 23 00 | GLASS MASONRY UNITS | samples | Samples — Glass Block: Full size units, each type required. |  |  | draft |  |  |  |  | 0
rc23-147 | 04 23 00 | GLASS MASONRY UNITS | samples | Samples — Reinforcement: 12 inch long, full section. |  |  | draft |  |  |  |  | 0
rc23-148 | 04 23 00 | GLASS MASONRY UNITS | samples | Samples — Color Mortar Sample: 5 inch square or 5 inch diameter sample. |  |  | draft |  |  |  |  | 0
rc23-149 | 04 23 00 | GLASS MASONRY UNITS | samples | Sample — Glass Block: Full size units, each type required. |  |  | draft |  |  |  |  | 0
rc23-150 | 04 23 00 | GLASS MASONRY UNITS | samples | Sample — Reinforcement: 12 inch long, full section. |  |  | draft |  |  |  |  | 0
rc23-151 | 04 23 00 | GLASS MASONRY UNITS | samples | Sample — Color Mortar Sample: 5 inch square or 5 inch diameter sample. |  |  | draft |  |  |  |  | 0
rc23-152 | 05 50 00 | METAL FABRICATIONS | certificates | Quality Control Submittals — Certificates: Copy of certificates required under Quality Assurance Article. |  |  | draft |  |  |  |  | 0
rc23-154 | 05 50 00 | METAL FABRICATIONS | other | Submittal — Manufacturer-provided EPDs must be Product Specific Type III (Third- Party Reviewed), in adherence with ISO 14025 Environmental labels and declarations, ISO 14044 Environmental management – Life cycle assessment, and ISO 21930 Core rules for environmental product declarations of construction products and services. |  |  | draft |  |  |  |  | 0
rc23-155 | 05 50 00 | METAL FABRICATIONS | shop_drawings | Shop Drawings: Show application to project. Furnish setting drawings and templates for installation of bolts and anchors in other Work. Indicate shop and field welds by standard AWS welding symbols in accordance with AWS A2.4. Updated 06/29/2023 Printed 12/17/2025 055000 - 1 Project No. 47444 – C. |  |  | draft |  |  |  |  | 0
rc23-156 | 06 10 00 | ROUGH CARPENTRY | certificates | Certification for wood treatments: Pressure Treatment certification by treating plant stating chemicals and process used, net amount of chemical preservative retained, and conformance with specified standards. | AWPA Standards for the treatment, Elco |  | draft |  |  |  |  | 0
rc23-157 | 06 17 53 | WOOD TRUSSES | design_data | Connector plate evaluation information, lumber design values, design calculations stamped and signed by a licensed Professional Engineer. |  |  | draft |  |  |  |  | 0
rc23-158 | 06 17 53 | WOOD TRUSSES | shop_drawings | Truss framing plans, truss elevations, locations and details of connector plates, bearing and anchorage details, bracing and connection details, species and grades of lumber, and connections required for the support of other work. |  |  | draft |  |  |  |  | 0
rc23-159 | 06 20 00 | FINISH CARPENTRY | shop_drawings | Shop drawings showing fabrication details and connections to adjacent Work. |  |  | draft |  |  |  |  | 0
rc23-160 | 07 05 43 | CLADDING SUPPORT SYSTEMS | certificates | Certification of structural performance without permanent deformation or failure of structural members in accordance with design wind velocities. | Advanced Architectural Products (A2P), CMH sub-framing support system manufacturer for CMH | GreenGirt CMH Sub-Framing System | draft |  |  |  |  | 0
rc23-161 | 07 05 43 | CLADDING SUPPORT SYSTEMS | design_data | Finite element analysis (FEA) report to model and evaluate areas of the longest composite girt cantilever span possible between intermediate framing members/attachment. | Advanced Architectural Products (A2P), CMH sub-framing support system manufacturer for CMH | GreenGirt CMH Sub-Framing System | draft |  |  |  |  | 0
rc23-162 | 07 05 43 | CLADDING SUPPORT SYSTEMS | product_data | Product Data: Submit for each product being used as indicated, including installation details, material descriptions, dimensions of individual components and profiles, and necessary accessories for a complete assembled system. | CMH sub-framing support system manufacturer for CMH |  | draft |  |  |  |  | 0
rc23-163 | 07 05 43 | CLADDING SUPPORT SYSTEMS | test_reports | Fire testing report in accordance with ASTM E119 test methods for CMH sub-framing support system. | Advanced Architectural Products (A2P), CMH sub-framing support system manufacturer for CMH | GreenGirt CMH Sub-Framing System | draft |  |  |  |  | 0
rc23-153 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | product_data | Product Data — Include waterproofing manufacturer's recommended details for flashings, joint treatment, and required protection. |  |  | draft |  |  |  |  | 0
rc23-164 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | certificates | Quality Control Submittals 1. Certificat — Certifications: Submit a letter certifying that the membrane material meets the requirements listed in the specifications. |  |  | draft |  |  |  |  | 0
rc23-165 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | certificates | Quality Control Submittals 1. Certificat — Installers Qualifications: a. Submit a letter certifying that the applicator has been actively installing waterproofing and/or roofing systems for the past 3 years. b. Submit the names and addresses of 5 previous waterproofing and/or roofing projects. Include the type and size of each project, the waterproofing and/or roofing manufacturer's name, and the name and telephone number of a contact person at the project location. c. Submit a letter certifying that the supervisor or foreman and the workers applying the waterproofing materials have at least 3 years experience in the application of waterproofing and/or roofing materials. |  |  | draft |  |  |  |  | 0
rc23-166 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | certificates | Certifications: A letter certifying that the membrane material meets the requirements listed in the specifications. |  |  | draft |  |  |  |  | 0
rc23-167 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | certificates | Installers Qualifications: A letter certifying that the applicator has been actively installing waterproofing and/or roofing systems for the past 3 years. |  |  | draft |  |  |  |  | 0
rc23-168 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | certificates | Submit the names and addresses of 5 previous waterproofing and/or roofing projects. Include the type and size of each project, the waterproofing and/or roofing manufacturer's name, and the name and telephone number of a contact person at the project location. |  |  | draft |  |  |  |  | 0
rc23-169 | 07 14 00 | LIQUID APPLIED WATERPROOFING SYSTEM | certificates | A letter certifying that the supervisor or foreman and the workers applying the waterproofing materials have at least 3 years experience in the application of waterproofing and/or roofing materials. |  |  | draft |  |  |  |  | 0
rc23-170 | 07 21 00 | BUILDING INSULATION | product_data | Product Data — Include data substantiating that the materials comply with the specified thermal resistance and vapor resistance qualities. |  |  | draft |  |  |  |  | 0
rc23-171 | 07 21 00 | BUILDING INSULATION | samples | Samples for each type: Blanket, Batt or Roll: 12 inch sq.; Rigid Type: 6 inch sq. |  |  | draft |  |  |  |  | 0
rc23-172 | 07 26 00 | VAPOR RETARDER UNDER SLABS ON GRADE | product_data | Catalog sheets, specifications, and installation instructions for each material specified. | Henry Company, Stego Industries, LLC., W. R. Meadows, Inc., Stego Industries, LLC, W. R. Meadows, Inc | Moistop Ultra 15, Stego Wrap 15-Mil Vapor Barrier, Perminator 15 Mil Underslab Vapor-Mat, Rating | draft |  |  |  |  | 0
rc23-173 | 07 27 00 | AIR BARRIERS | certificates | Product Certificates: From air-barrier manufacturer, certifying compatibility of air barriers and accessory materials with Project materials that connect to or that come in contact with the barrier. Printed 12/17/2025 072700 - 1 Project No. 47444 – C. |  |  | draft |  |  |  |  | 0
rc23-174 | 07 27 00 | AIR BARRIERS | product_data | Product Data — Include manufacturer's written instructions for evaluating, preparing, and treating each substrate; technical data; dry film thickness; and tested physical and performance properties of products. |  |  | draft |  |  |  |  | 0
rc23-175 | 07 27 00 | AIR BARRIERS | shop_drawings | Shop Drawings — Show locations and extent of air-barrier materials, accessories, and assemblies specific to Project conditions. |  |  | draft |  |  |  |  | 0
rc23-176 | 07 27 00 | AIR BARRIERS | shop_drawings | Shop Drawings — Include details for substrate joints and cracks, counterflashing strips, penetrations, inside and outside corners, terminations, and tie-ins with adjoining construction. |  |  | draft |  |  |  |  | 0
rc23-177 | 07 27 00 | AIR BARRIERS | shop_drawings | Shop Drawings — Include details of interfaces with other materials that form part of air barrier. |  |  | draft |  |  |  |  | 0
rc23-178 | 07 41 13 | PREFORMED METAL SOFFIT SYSTEM | certificates | Contract Closeout Submittals — Warranties: Specified warranties. | ATAS International |  | draft |  |  |  |  | 0
rc23-179 | 07 41 13 | PREFORMED METAL SOFFIT SYSTEM | product_data | Submittals Package: Submit product data, shop drawings, and any proposed deviations from the Contract Documents, at the same time as one complete package. Partial submittals will not be considered. | ATAS International |  | draft |  |  |  |  | 0
rc23-180 | 07 41 13 | PREFORMED METAL SOFFIT SYSTEM | samples | Color Samples for Initial Selection: Panel manufacturer’s standard range of colors for finish specified. | ATAS International |  | draft |  |  |  |  | 0
rc23-181 | 07 41 13 | PREFORMED METAL SOFFIT SYSTEM | samples | Samples for Verification — Soffit Panel: Full panel width, 12 inches long, each type. | ATAS International |  | draft |  |  |  |  | 0
rc23-182 | 07 41 13 | PREFORMED METAL SOFFIT SYSTEM | samples | Samples for Verification — Include closures, trim, and other metal panel accessories. | ATAS International |  | draft |  |  |  |  | 0
rc23-183 | 07 42 43 | COMPOSITE WALL PANELS | certificates | Warranties: Final material and finish warranties. |  |  | draft |  |  |  |  | 0
rc23-184 | 07 42 43 | COMPOSITE WALL PANELS | manuals | Maintenance Data: For composite panels to include in maintenance manuals. |  |  | draft |  |  |  |  | 0
rc23-185 | 07 42 43 | COMPOSITE WALL PANELS | product_data | Product Data — Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for each type of panel and accessory. Printed 12/17/2025 074243 - 1 Project No. 47444 – C |  |  | draft |  |  |  |  | 0
rc23-186 | 07 42 43 | COMPOSITE WALL PANELS | samples | Samples for Verification — Composite Panels: 12 inches long by actual panel width. Include fasteners, closures, and other composite panel accessories. Submit custom color samples in paint manufacturer's standard size. |  |  | draft |  |  |  |  | 0
rc23-187 | 07 42 43 | COMPOSITE WALL PANELS | samples | Samples for Verification — Trim: 12 inches long section of trim in each finish and color required. |  |  | draft |  |  |  |  | 0
rc23-188 | 07 42 43 | COMPOSITE WALL PANELS | samples | Samples for Initial Selection — Include similar Samples of trim and accessories involving color selection. |  |  | draft |  |  |  |  | 0
rc23-189 | 07 42 43 | COMPOSITE WALL PANELS | samples | Sample Warranties: For special warranties. |  |  | draft |  |  |  |  | 0
rc23-190 | 07 42 43 | COMPOSITE WALL PANELS | shop_drawings | Shop Drawings — Include details of panel dimensions, profiles, edge conditions, joints, corners, anchorages, attachment assembly, trim, flashings, closures, and accessories; and special details. |  |  | draft |  |  |  |  | 0
rc23-191 | 07 42 43 | COMPOSITE WALL PANELS | shop_drawings | Shop Drawings — Accessories: Include details of the flashing, trim, and anchorage, at a scale of not less than 1-1/2 inches per 12 inches. |  |  | draft |  |  |  |  | 0
rc23-192 | 07 42 43 | COMPOSITE WALL PANELS | test_reports | Product Test Reports — Composite Manufacturer's Material Test Reports: Certified test reports showing compliance with specific performance or third-party listing documenting compliance to comparable code sections IBC 1404.16.1 and IBC 1703.5. |  |  | draft |  |  |  |  | 0
rc23-193 | 07 61 00 | SHEET METAL ROOFING | product_data | Product Data — Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for each type of panel and accessory. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-194 | 07 61 00 | SHEET METAL ROOFING | product_data | Product Data — Include product test reports performed by a qualified testing agency. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-195 | 07 61 00 | SHEET METAL ROOFING | samples | Samples — Sheet metal: 6 inches square, each type. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-196 | 07 61 00 | SHEET METAL ROOFING | samples | Samples — Fasteners and other accessories: 3, each type. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-197 | 07 61 00 | SHEET METAL ROOFING | samples | Samples — Sealant: One cartridge. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-198 | 07 61 00 | SHEET METAL ROOFING | samples | Sample Warranties: For special warranties. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-199 | 07 61 00 | SHEET METAL ROOFING | shop_drawings | Shop Drawings — Include fabrication and installation layouts of metal panels; details of edge conditions, joints, panel profiles, corners, anchorages, attachment system, trim, flashings, closures, and accessories; and special details. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-200 | 07 61 00 | SHEET METAL ROOFING | shop_drawings | Shop Drawings — Accessories: Include details of the flashing, trim, and anchorage systems, at a scale of not less than 1-1/2 inches per 12 inches. | Architect from manufacturer's full range | AZ50 coating designation | draft |  |  |  |  | 0
rc23-201 | 07 71 23 | GUTTERS AND DOWNSPOUTS | product_data | Product Data: Catalog sheets, colors, specifications, and installation instructions for each material specified. |  |  | draft |  |  |  |  | 0
rc23-202 | 07 71 23 | GUTTERS AND DOWNSPOUTS | samples | Samples — Gutter: 12 inches long, full section. |  |  | draft |  |  |  |  | 0
rc23-203 | 07 71 23 | GUTTERS AND DOWNSPOUTS | samples | Samples — Downspout: 12 inches long, full section. |  |  | draft |  |  |  |  | 0
rc23-204 | 07 71 23 | GUTTERS AND DOWNSPOUTS | samples | Samples — Hanger Brackets, Braces, and Stiffeners: One, each type. |  |  | draft |  |  |  |  | 0
rc23-205 | 07 71 23 | GUTTERS AND DOWNSPOUTS | samples | Samples — Fasteners: Six, each type. |  |  | draft |  |  |  |  | 0
rc23-206 | 07 71 23 | GUTTERS AND DOWNSPOUTS | samples | Samples — Color Samples: 6 inches by 6 inches of each color and finish as selected. |  |  | draft |  |  |  |  | 0
rc23-207 | 07 71 23 | GUTTERS AND DOWNSPOUTS | shop_drawings | Shop Drawings: Show method of forming, jointing, and securing the gutters and downspouts. Include attachment to adjoining construction. |  |  | draft |  |  |  |  | 0
rc23-208 | 07 92 00 | JOINT SEALERS | product_data | Product Data: Catalog sheets, specifications, and installation instructions for each product specified except miscellaneous materials. |  |  | draft |  |  |  |  | 0
rc23-209 | 07 92 00 | JOINT SEALERS | samples | Samples for Initial Selection: Manufacturer's color charts consisting of strips of cured sealants showing the full range of colors available for each product exposed to view. |  |  | draft |  |  |  |  | 0
rc23-210 | 07 92 00 | JOINT SEALERS | samples | Samples for each type required — Sealants: One pint or standard tube. |  |  | draft |  |  |  |  | 0
rc23-211 | 07 92 00 | JOINT SEALERS | samples | Samples for each type required — Joint Primer/Sealer/Conditioners: One pint. |  |  | draft |  |  |  |  | 0
rc23-212 | 07 92 00 | JOINT SEALERS | samples | Samples for each type required — Backer Rods: 24 inch long full section. |  |  | draft |  |  |  |  | 0
rc23-213 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | certificates | Certificate — Certification of Compliance as described in the Quality Assurance Article. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-214 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | certificates | Certificate — Company Field Advisor’s Qualification Data a. Name of Company Field Advisor and Employer’s name, business address and telephone number and e-mail address. b. Names and addresses of 3 similar projects Company Field Advisor has worked on during the past three years. c. Written certification on steel door and frame manufacturer’s letterhead that Company Field advisor is technically qualified in design, installation, and servicing of the products furnished for this Project. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-215 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | certificates | Certificate — Certified Supervisor’s and Installer’s Qualification Data a. Name of Supervisor and each Installer performing Work, and Employer’s name, business address and telephone number. b. Names and addresses of 3 similar projects Supervisor and each Installer has worked on during the past three years. c. Written certification on steel door and frame manufacturer’s letterhead that Supervisor/Installer is technically qualified to ensure approved steel frames and doors are installed, adjusted, and operate properly. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-216 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | product_data | The manufacturer’s installation instructions shall be provided along with product data. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-217 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Details of each different wall opening condition. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-218 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | product_data | Product Data — Include construction details, material descriptions, core descriptions, and finishes. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-219 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | samples | Samples for Initial Selection: For Pultruded Fiberglass with factory-applied color finishes. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-220 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | samples | Samples for Verification — Finishes: For each type of exposed finish required, prepared on Samples of not less than 3 by 5 inches. Updated 2-5-2025 Printed 12/17/2025 081613-2 Project No. 47444 - C | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-221 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | samples | Samples for Verification — Fabrication: Prepare Samples approximately 12 by 12 inches to demonstrate compliance with requirements for quality of materials and construction: a. Doors: Show vertical-edge, top, and bottom construction; core construction; and hinge and other applied hardware reinforcement. Include separate section showing glazing if applicable. b. Frames: Show profile, corner joint, floor and wall anchors, and silencers. Include separate section showing fixed hollow-metal panels and glazing if applicable. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-222 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Elevations of each door type. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-223 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Details of doors, including vertical- and horizontal-edge details and metal thicknesses. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-224 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Frame details for each frame type, including dimensioned profiles and metal thicknesses. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-225 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Locations of reinforcement and preparations for hardware. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-227 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Details of electrical raceway and preparation for electrified hardware, access control systems, and security systems. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-228 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Details of anchorages, joints, field splices, and connections. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-229 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Details of accessories. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-230 | 08 16 13 | FIBERGLASS DOORS AND FRAMES | shop_drawings | Shop Drawings — Details of moldings, removable stops, and glazing. | GC and installed by experienced mechanics |  | draft |  |  |  |  | 0
rc23-231 | 08 51 13 | ALUMINUM WINDOWS | product_data | Product Data: Catalog sheets, specifications, and installation instructions for each type window unit. |  |  | draft |  |  |  |  | 0
rc23-232 | 08 51 13 | ALUMINUM WINDOWS | samples | Samples — Corner section of frame, sash, and insect screen. |  |  | draft |  |  |  |  | 0
rc23-233 | 08 51 13 | ALUMINUM WINDOWS | samples | Samples — Color Samples: Manufacturer’s standard color finishes. |  |  | draft |  |  |  |  | 0
rc23-234 | 08 51 13 | ALUMINUM WINDOWS | shop_drawings | Shop Drawings: Show fabrication details and connections to adjacent construction. |  |  | draft |  |  |  |  | 0
rc23-235 | 08 71 00 | DOOR HARDWARE | certificates | Product Certificates — Certify that door hardware for use on each type and size of labeled fire-rated doors complies with listed fire-rated door assemblies. |  |  | draft |  |  |  |  | 0
rc23-236 | 08 71 00 | DOOR HARDWARE | manuals | Maintenance Data: For each type of door hardware to include in maintenance manuals. |  |  | draft |  |  |  |  | 0
rc23-237 | 08 71 00 | DOOR HARDWARE | product_data | The manufacturers’ installation instructions shall be provided along with product data. |  |  | draft |  |  |  |  | 0
rc23-239 | 08 71 00 | DOOR HARDWARE | product_data | Product Data — Include construction details, material descriptions, dimensions of individual components and profiles, and finishes. |  |  | draft |  |  |  |  | 0
rc23-240 | 08 71 00 | DOOR HARDWARE | samples | Samples — Tag Samples with full product description to coordinate Samples with door hardware schedule. |  |  | draft |  |  |  |  | 0
rc23-241 | 08 71 00 | DOOR HARDWARE | samples | Samples for Initial Selection: For each type of exposed finish. |  |  | draft |  |  |  |  | 0
rc23-242 | 08 71 00 | DOOR HARDWARE | samples | Samples for Verification — Sample Size: Full-size units or minimum 2-by-4-inch Samples for sheet and 4-inch-long Samples for other products. a. Full-size Samples will be returned to Contractor. Units that are acceptable and remain undamaged through submittal, review, and field comparison process may, after final check of operation, be incorporated into the Work, within limitations of keying requirements. |  |  | draft |  |  |  |  | 0
rc23-243 | 08 71 00 | DOOR HARDWARE | samples | Samples for Verification — Tag Samples with full product description to coordinate Samples with door hardware schedule. |  |  | draft |  |  |  |  | 0
rc23-244 | 08 71 00 | DOOR HARDWARE | samples | Sample Warranty: For special warranty. |  |  | draft |  |  |  |  | 0
rc23-245 | 08 71 00 | DOOR HARDWARE | shop_drawings | Shop Drawings — Include diagrams for power, signal, and control wiring. |  |  | draft |  |  |  |  | 0
rc23-246 | 08 71 00 | DOOR HARDWARE | shop_drawings | Shop Drawings — Include details of the interface of electrified door hardware and building safety and security systems. |  |  | draft |  |  |  |  | 0
rc23-247 | 08 71 00 | DOOR HARDWARE | test_reports | Product Test Reports: For compliance with accessibility requirements, for tests performed by manufacturer and witnessed by a qualified testing agency, for door hardware on doors located in accessible routes. |  |  | draft |  |  |  |  | 0
rc23-238 | 09 21 16 | GYPSUM BOARD SYSTEMS | product_data | Catalog sheets, specifications, and installation instructions for each item specified. | ITW Buildex |  | draft |  |  |  |  | 0
rc23-006 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Main Beams. |  |  | draft |  |  |  |  | 0
rc23-008 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Cross Channels. |  |  | draft |  |  |  |  | 0
rc23-009 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Channel Mold. |  |  | draft |  |  |  |  | 0
rc23-010 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Cross Tees. |  |  | draft |  |  |  |  | 0
rc23-039 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Hangers. |  |  | draft |  |  |  |  | 0
rc23-248 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Main Beams. |  | Main Beams, Cross Channels, Channel Mold, Cross Tees, Hangers | draft |  |  |  |  | 0
rc23-249 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Cross Channels. |  | Main Beams, Cross Channels, Channel Mold, Cross Tees, Hangers | draft |  |  |  |  | 0
rc23-250 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Channel Mold. |  | Main Beams, Cross Channels, Channel Mold, Cross Tees, Hangers | draft |  |  |  |  | 0
rc23-251 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Cross Tees. |  | Main Beams, Cross Channels, Channel Mold, Cross Tees, Hangers | draft |  |  |  |  | 0
rc23-252 | 09 22 14 | FURRING FOR GYPSUM BOARD CEILINGS | product_data | Product Data — Hangers. |  | Main Beams, Cross Channels, Channel Mold, Cross Tees, Hangers | draft |  |  |  |  | 0
rc23-253 | 09 67 23 | EPOXY RESIN FLOORING | product_data | Product Data — Manufacturer’s product data for primers, underlayments, base coats, seal coats, and broadcast medium. | Elite Crete Systems, 1061 Transport Drive, Valparaiso, IN 46383, 323-4445, www.elitecrete.com;, comparable products by one of the following |  | draft |  |  |  |  | 0
rc23-254 | 09 67 23 | EPOXY RESIN FLOORING | product_data | Product Data — Manufacturer’s storage and installation instructions. | Elite Crete Systems, 1061 Transport Drive, Valparaiso, IN 46383, 323-4445, www.elitecrete.com;, comparable products by one of the following |  | draft |  |  |  |  | 0
rc23-255 | 09 67 23 | EPOXY RESIN FLOORING | samples | Samples for Initial Selection: 3 inch x 3 inch color samples showing the manufacturer’s full range of available colors. | Elite Crete Systems, 1061 Transport Drive, Valparaiso, IN 46383, 323-4445, www.elitecrete.com;, comparable products by one of the following |  | draft |  |  |  |  | 0
rc23-256 | 09 67 23 | EPOXY RESIN FLOORING | samples | Samples: 12 inch x 12 inch samples of each type of resinous floor system including cove base and joint sealant specified to show color and texture with specified coats cascaded. Updated 06/1/2024 Printed 12/17/2025 096723 - 1 Project No. 47444 – C. | Elite Crete Systems, 1061 Transport Drive, Valparaiso, IN 46383, 323-4445, www.elitecrete.com;, comparable products by one of the following |  | draft |  |  |  |  | 0
rc23-258 | 09 67 23 | EPOXY RESIN FLOORING | test_reports | Test and Evaluation Reports: When requested by the Director’s Representative, submit certified test reports showing compliance with specified performance characteristics and physical properties. | Elite Crete Systems, 1061 Transport Drive, Valparaiso, IN 46383, 323-4445, www.elitecrete.com;, comparable products by one of the following |  | draft |  |  |  |  | 0
rc23-259 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | manuals | Contract Closeout Submittals — Maintenance Data: Deliver 2 copies, covering the installed products, to the Director's Representative. |  |  | draft |  |  |  |  | 0
rc23-260 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | product_data | Product Data — Catalog sheets, specifications, and installation instructions for each material specified. |  |  | draft |  |  |  |  | 0
rc23-261 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | product_data | Product Data — Physical property data for plastic panels. |  |  | draft |  |  |  |  | 0
rc23-262 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | samples | Samples — Plastic Panels: 12 inch square pieces. |  |  | draft |  |  |  |  | 0
rc23-263 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | samples | Samples — Accessories and Moldings: 12 inches long, full section, each type. |  |  | draft |  |  |  |  | 0
rc23-264 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | samples | Samples — Fasteners: One, each type. |  |  | draft |  |  |  |  | 0
rc23-265 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | samples | Samples — Adhesive: One pint, or standard size tube. |  |  | draft |  |  |  |  | 0
rc23-266 | 09 77 23 | FIBER REINFORCED PLASTIC PANELS | samples | Samples — Color Samples: Plastic panel manufacturer's standard colors and textures. |  |  | draft |  |  |  |  | 0
rc23-267 | 09 91 01 | CONSTRUCTION PAINTING | certificates | List of each paint product to be delivered and installed, including written certification stating that each paint product listed complies with the VOC regulatory requirements. |  |  | draft |  |  |  |  | 0
rc23-268 | 09 91 01 | CONSTRUCTION PAINTING | other | Painting Schedule listing all exterior and interior substrates to be painted and specified finish paint type designation; product name and manufacturer, recommended primers and product numbers, and finish paint color designation for each substrate. |  |  | draft |  |  |  |  | 0
rc23-269 | 09 91 01 | CONSTRUCTION PAINTING | product_data | Product Data Sheets — Percent solids by weight and volume, solvent, vehicle, weight per gallon, ASTM D 523 gloss/reflectance angle, recommended wet and dry film thickness, volatile organic compound (VOC) content in lbs/gallon, product use limitations and environmental restrictions, substrate surface preparation methods, directions and precautions for mixing and thinning, recommended application methods, square foot area coverage per gallon, storage instructions, and shelf-life expiration date. |  |  | draft |  |  |  |  | 0
rc23-270 | 09 91 01 | CONSTRUCTION PAINTING | product_data | Product Data Sheets — Manufacturer’s recommended primer for each finish paint product and substrate to be painted. |  |  | draft |  |  |  |  | 0
rc23-271 | 09 91 01 | CONSTRUCTION PAINTING | product_data | Product Data Sheets — Manufacturer’s complete range of available colors for each finish paint product to be applied. Updated 01/23/2012 Printed 12/17/2025 099101 - 1 Project No. 47444 – C |  |  | draft |  |  |  |  | 0
rc23-272 | 09 91 01 | CONSTRUCTION PAINTING | product_data | Manufacturer’s published product data sheets describing percent solids by weight and volume, solvent, vehicle, weight per gallon, ASTM D 523 gloss/reflectance angle, recommended wet and dry film thickness, VOC content, product use limitations, substrate surface preparation methods, directions and precautions for mixing and thinning, recommended application methods, square foot area coverage per gallon, storage instructions, and shelf-life expiration date. | Benjamin Moore, PPG, Sherwin-Williams |  | draft |  |  |  |  | 0
rc23-273 | 09 91 01 | CONSTRUCTION PAINTING | samples | Two finish paint samples applied over recommended primers for each substrate to be painted in designated color and specified ASTM D 523 reflectance. |  |  | draft |  |  |  |  | 0
rc23-274 | 09 91 01 | CONSTRUCTION PAINTING | test_reports | Certified test results from an independent testing laboratory, showing that products submitted comply with the specifications, when requested by the Director’s Representative. |  |  | draft |  |  |  |  | 0
rc23-257 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | samples | Samples for Initial Selection — Include representative Samples of available typestyles and graphic symbols. |  |  | draft |  |  |  |  | 0
rc23-275 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | manuals | Maintenance Data: For signs to include in maintenance manuals. |  |  | draft |  |  |  |  | 0
rc23-276 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | product_data | Product Data: For each type of product. |  |  | draft |  |  |  |  | 0
rc23-277 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | samples | Samples for Verification — Dimensional Characters: Full-size Sample of each type of dimensional character. |  |  | draft |  |  |  |  | 0
rc23-278 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | samples | Samples for Verification — Exposed Accessories: Full-size Sample of each accessory type. |  |  | draft |  |  |  |  | 0
rc23-279 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | samples | Samples for Verification — Full-size Samples, if approved, will be returned to Contractor for use in the Project. |  |  | draft |  |  |  |  | 0
rc23-280 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | shop_drawings | Shop Drawings — Include fabrication and installation details and attachments to other work. |  |  | draft |  |  |  |  | 0
rc23-281 | 10 14 19 | DIMENSIONAL LETTER SIGNAGE | shop_drawings | Shop Drawings — Show sign mounting heights, locations of supplementary supports to be provided by other installers, and accessories. |  |  | draft |  |  |  |  | 0
rc23-282 | 10 14 23 | SIGNS | product_data | Product Data: Catalog sheets, specifications, and installation instructions for each sign type and mounting type specified. |  |  | draft |  |  |  |  | 0
rc23-283 | 10 14 23 | SIGNS | samples | Samples — Full size of each sign type and copy type specified including mounting accessories. These samples will be returned and, if approved, may be used in the Work. |  |  | draft |  |  |  |  | 0
rc23-284 | 10 14 23 | SIGNS | samples | Samples — Color Samples: Manufacturer’s standard colors for sign material and finishes specified. |  |  | draft |  |  |  |  | 0
rc23-285 | 10 14 23 | SIGNS | shop_drawings | Shop Drawings: Show fabrication and mounting details for each sign type and copy specified. Include sign designs, dimensions, copy style, and copy heights. |  |  | draft |  |  |  |  | 0
rc23-004 | 10 21 13 | METAL TOILET COMPARTMENTS | product_data | Product Data — Screens, types specified. |  |  | draft |  |  |  |  | 0
rc23-005 | 10 21 13 | METAL TOILET COMPARTMENTS | product_data | Product Data — Hardware and accessories. |  |  | draft |  |  |  |  | 0
rc23-286 | 10 21 13 | METAL TOILET COMPARTMENTS | product_data | Product Data — Panels and Doors. |  |  | draft |  |  |  |  | 0
rc23-287 | 10 21 13 | METAL TOILET COMPARTMENTS | product_data | Product Data — Pilasters, types specified. |  |  | draft |  |  |  |  | 0
rc23-288 | 10 21 13 | METAL TOILET COMPARTMENTS | samples | Samples — Hardware: One, each item and type specified. |  |  | draft |  |  |  |  | 0
rc23-289 | 10 21 13 | METAL TOILET COMPARTMENTS | samples | Samples — Panels: One 12 inch square corner section. |  |  | draft |  |  |  |  | 0
rc23-290 | 10 21 13 | METAL TOILET COMPARTMENTS | samples | Samples — Pilaster Leveling Device: One complete device, including pilaster shoe. |  |  | draft |  |  |  |  | 0
rc23-291 | 10 21 13 | METAL TOILET COMPARTMENTS | samples | Samples — Bracket Fittings: One each type. |  |  | draft |  |  |  |  | 0
rc23-292 | 10 21 13 | METAL TOILET COMPARTMENTS | samples | Samples — Fasteners: One each type. |  |  | draft |  |  |  |  | 0
rc23-293 | 10 21 13 | METAL TOILET COMPARTMENTS | shop_drawings | Shop Drawings: Show fabrication details and connections to adjacent work. |  |  | draft |  |  |  |  | 0
rc23-294 | 10 28 13 | TOILET AND BATH ACCESSORIES | manuals | Contract Closeout Submittals — Operation and maintenance data. | Updated, Koala Kare | No. KB110-SSWM by Koala Kare. | draft |  |  |  |  | 0
rc23-295 | 10 28 13 | TOILET AND BATH ACCESSORIES | manuals | Contract Closeout Submittals — Parts list. | Updated, Koala Kare | No. KB110-SSWM by Koala Kare. | draft |  |  |  |  | 0
rc23-296 | 10 28 13 | TOILET AND BATH ACCESSORIES | manuals | Contract Closeout Submittals — Keys and tools. | Updated, Koala Kare | No. KB110-SSWM by Koala Kare. | draft |  |  |  |  | 0
rc23-297 | 10 28 13 | TOILET AND BATH ACCESSORIES | product_data | Product Data: Specifications or data sheets and installation instructions for each product required. | Updated, Koala Kare | No. KB110-SSWM by Koala Kare. | draft |  |  |  |  | 0
rc23-298 | 10 28 13 | TOILET AND BATH ACCESSORIES | samples | Samples: One full size sample of each product required, unless otherwise specified, complete with mounting devices and fasteners. These samples will be returned unless otherwise specified. If approved, samples may be used in the Work. | Updated, Koala Kare | No. KB110-SSWM by Koala Kare. | draft |  |  |  |  | 0
rc23-299 | 10 28 14 | ELECTRIC HAND DRYERS | closeout | Operation & Maintenance Data: Deliver 2 copies, covering the installed product. |  |  | draft |  |  |  |  | 0
rc23-300 | 10 28 14 | ELECTRIC HAND DRYERS | product_data | Product Data: Catalog sheets, specifications and installation instructions. |  |  | draft |  |  |  |  | 0
rc23-301 | 10 28 14 | ELECTRIC HAND DRYERS | product_data | Catalog sheets, specifications and installation instructions for electric hand dryers. | Excel Dryer Inc., American Specialties, Inc., Bobrick Washroom Equipment, Inc., World Dryer Corporation | XLERATOR® Hand Dryer | draft |  |  |  |  | 0
rc23-302 | 11 19 01 |  | certificates | Environmental Product Declaration (EPD) from the manufacturer for concrete and steel, if available. A statement of the contractor’s good faith effort to obtain the EPD shall be provided if not available. | Allied Tube & Conduit Corp, American Tube and Pipe Co, Sonoco Products Co, Jefferson Smurfit Corp |  | draft |  |  |  |  | 0
rc23-303 | 11 19 01 |  | product_data | Manufacturer’s catalog cuts, specifications, and installation instructions for each item specified. | Allied Tube & Conduit Corp, American Tube and Pipe Co, Sonoco Products Co, Jefferson Smurfit Corp |  | draft |  |  |  |  | 0
rc23-304 | 11 19 01 |  | shop_drawings | Complete detailed drawings for each height and style of fence and gate required. Include separate schedule for each listing all materials required and technical data such as size, weight, and finish. | Allied Tube & Conduit Corp, American Tube and Pipe Co, Sonoco Products Co, Jefferson Smurfit Corp |  | draft |  |  |  |  | 0
rc23-002 | 31 00 00 | EARTHWORK | samples | Samples — Selected Fill: 40 - 50 lb. |  |  | draft |  |  |  |  | 0
rc23-003 | 31 00 00 | EARTHWORK | samples | Samples — Cushion Material: 30 lb. |  |  | draft |  |  |  |  | 0
rc23-226 | 31 00 00 | EARTHWORK | samples | Samples — Subbase Course Type 2: 50 - 60 lb. (Two Samples). |  |  | draft |  |  |  |  | 0
rc23-305 | 31 00 00 | EARTHWORK | other | Excavation Procedure: Layout drawing or detailed outline of intended excavation procedure. |  |  | draft |  |  |  |  | 0
rc23-306 | 31 00 00 | EARTHWORK | other | Subbase Materials: Name and location of source and the DOT Source Number. |  |  | draft |  |  |  |  | 0
rc23-307 | 31 00 00 | EARTHWORK | other | Other Aggregates: Name and location of source and soil laboratory test results. |  |  | draft |  |  |  |  | 0
rc23-308 | 31 00 00 | EARTHWORK | product_data | Product Data — Filter Fabric: Manufacturer’s catalog sheets, specifications, and installation instructions. |  |  | draft |  |  |  |  | 0
rc23-309 | 31 00 00 | EARTHWORK | product_data | Filter Fabric: Manufacturer’s catalog sheets, specifications, and installation instructions. | Amoco, Maccaferri, Mirafi, Fiberweave | Amoco 1199, Amoco 2019, Maccaferri MacTex MX140, Maccaferri MacTex MX155, Mirafi 140N, Mirafi 160N, Fiberweave 403, Fiberweave 404 | draft |  |  |  |  | 0
rc23-310 | 31 00 00 | EARTHWORK | samples | Samples — Select Granular Material: 50 - 60 lb. (Two Samples). |  |  | draft |  |  |  |  | 0
rc23-311 | 31 00 00 | EARTHWORK | samples | Samples of Select Granular Material (50 - 60 lb., Two Samples), Subbase Course Type 2 (50 - 60 lb., Two Samples), Selected Fill (40 - 50 lb.), Cushion Material (30 lb.). |  |  | draft |  |  |  |  | 0
rc23-312 | 31 13 00 | SELECTIVE TREE REMOVAL AND TRIMMING | other | Detailed experience and qualifications description of tree trimming and removal, including types of equipment and experience. |  |  | draft |  |  |  |  | 0
rc23-313 | 32 12 16 | ASPHALT PAVING | certificates | Environmental Product Declaration (EPD) from the manufacturer for concrete within this specification section, if available. |  |  | draft |  |  |  |  | 0
rc23-314 | 32 12 16 | ASPHALT PAVING | other | Submittal — At the time of delivery, a copy of the delivery ticket must be presented to the Director’s Representative with the following minimum information: a. Ticket Number. b. Plant Identification. c. Project Name. d. Mix Type. e. Quantity of material in vehicle. f. Date and Time. |  |  | draft |  |  |  |  | 0
rc23-315 | 32 12 16 | ASPHALT PAVING | other | Pavement Quality Control Submittals — At the time of delivery, a copy of the delivery ticket must be presented to the Director’s Representative with the following minimum information: a. Ticket Number. b. Plant Identification. c. Project Name. d. Mix Type. e. Quantity of material in vehicle. f. Date and Time. |  |  | draft |  |  |  |  | 0
rc23-316 | 32 12 16 | ASPHALT PAVING | product_data | Asphaltic Pavement: Include mix design from NYSDOT approved Batch Plant, Mix Design Test results that are less than 6 months old. |  |  | draft |  |  |  |  | 0
rc23-317 | 32 13 00 | CONCRETE WALKS | other | Environmental Product Declaration (EPD) from the manufacturer for asphalt this specification section, if available. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-319 | 32 13 00 | CONCRETE WALKS | product_data | Product Data — Concrete Design Mix: Submit proposed concrete design mix together with name and location of batching plant at least 28 days prior to the start of concrete work. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-320 | 32 13 00 | CONCRETE WALKS | product_data | Product Data — Portland Cement: Brand and Manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-321 | 32 13 00 | CONCRETE WALKS | product_data | Product Data — Air-entraining Admixture: Brand and manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-322 | 32 13 00 | CONCRETE WALKS | product_data | Product Data — Water-reducing or High Range Water-reducing Admixture: Brand and manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-323 | 32 13 00 | CONCRETE WALKS | product_data | Product Data — Curing and Anti-Spalling Compound: Manufacturer’s specifications and application instructions. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-324 | 32 13 00 | CONCRETE WALKS | product_data | Product Data — ADA Detectable Warning Surface: Manufacturer’s specifications, product data, test reports, method of installation, and maintenance instructions. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-325 | 32 13 00 | CONCRETE WALKS | product_data | Concrete Design Mix: proposed concrete design mix together with name and location of batching plant. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-326 | 32 13 00 | CONCRETE WALKS | product_data | Portland Cement — Air-entraining Admixture: Brand and manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-327 | 32 13 00 | CONCRETE WALKS | product_data | Portland Cement — Water-reducing or High Range Water-reducing Admixture: Brand and manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-328 | 32 13 00 | CONCRETE WALKS | product_data | Portland Cement — Curing and Anti-Spalling Compound: Manufacturer’s specifications and application instructions. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-329 | 32 13 00 | CONCRETE WALKS | product_data | Portland Cement — ADA Detectable Warning Surface: Manufacturer’s specifications, product data, test reports, method of installation, and maintenance instructions. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-330 | 32 13 00 | CONCRETE WALKS | product_data | Air-entraining Admixture — Water-reducing or High Range Water-reducing Admixture: Brand and manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-331 | 32 13 00 | CONCRETE WALKS | product_data | Air-entraining Admixture — Curing and Anti-Spalling Compound: Manufacturer’s specifications and application instructions. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-332 | 32 13 00 | CONCRETE WALKS | product_data | Air-entraining Admixture — ADA Detectable Warning Surface: Manufacturer’s specifications, product data, test reports, method of installation, and maintenance instructions. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-333 | 32 13 00 | CONCRETE WALKS | product_data | Water-reducing or High Range Water-reducing Admixture: Brand and manufacturer’s name. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-335 | 32 13 00 | CONCRETE WALKS | product_data | Curing and Anti-Spalling Compound: Manufacturer’s specifications and application instructions. | Kaufman Products, Inc., Symons Corp., Sonneborn/ BASF Building Systems, Dayton Superior Corp., Master Builders/ BASF Building Systems, Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company | SureCure Emulsion, Cure & Seal, Kure-N-Seal, Day-Chem Cure & Seal UV, Acrylseal HS | draft |  |  |  |  | 0
rc23-336 | 32 13 00 | CONCRETE WALKS | product_data | ADA Detectable Warning Surface: Manufacturer’s specifications, product data, test reports, method of installation, and maintenance instructions. | Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company, Symons Corp, Dayton Superior Corp | Detectable Warning Plate Model R-4984, ADA Pavers, Detectable Warning Surface System, Classic Dot Detectable Warning Pavers, Granite Truncated Dome Pavers | draft |  |  |  |  | 0
rc23-337 | 32 13 00 | CONCRETE WALKS | samples | Bar Supports: Full size. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-338 | 32 13 00 | CONCRETE WALKS | samples | Bar Reinforcement: 12 inch minimum. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-339 | 32 13 00 | CONCRETE WALKS | samples | ADA Detectable Warning Surface: Two samples, the same color as the material to be installed, 6 inches x 8 inches minimum. | Symons Corp, Dayton Superior Corp, Neenah Foundry, Whiteacre-Greer, Detecto-Tile, Oaks Concrete Products, Cold Spring Granite Company |  | draft |  |  |  |  | 0
rc23-340 | 32 13 16 | IMPRINTED CONCRETE PAVING | design_data | Design Mixes: For each type of concrete. | Sika Corporation |  | draft |  |  |  |  | 0
rc23-341 | 32 13 16 | IMPRINTED CONCRETE PAVING | product_data | Product Data — Dry-shake colored hardener | Sika Corporation |  | draft |  |  |  |  | 0
rc23-342 | 32 13 16 | IMPRINTED CONCRETE PAVING | product_data | Product Data — Antiquing release agent | Sika Corporation |  | draft |  |  |  |  | 0
rc23-343 | 32 13 16 | IMPRINTED CONCRETE PAVING | product_data | Product Data — Liquid release agent | Sika Corporation |  | draft |  |  |  |  | 0
rc23-344 | 32 13 16 | IMPRINTED CONCRETE PAVING | product_data | Product Data — Imprinting/Texturing tools | Sika Corporation |  | draft |  |  |  |  | 0
rc23-345 | 32 13 16 | IMPRINTED CONCRETE PAVING | product_data | Product Data — Curing compound and sealer Printed 12/17/2025 321316 -1 Project No. 47444 - C | Sika Corporation |  | draft |  |  |  |  | 0
rc23-346 | 32 13 16 | IMPRINTED CONCRETE PAVING | samples | Samples for Initial Selection: Manufacturer’s color charts showing full range of colors available. | Sika Corporation |  | draft |  |  |  |  | 0
rc23-347 | 33 11 02 | PLASTIC WATER PIPE AND FITTINGS | product_data | Manufacturer’s specifications with detailed information regarding dimensions, pressure rating, fittings and installation instructions. Manufacturer’s data must indicate compliance with the standards specified herein. | National Sanitation Foundation (NSF) | PEX 1006 Polyethylene (HDPE) | draft |  |  |  |  | 0
rc23-348 | 33 13 00 | DISINFECTION OF WATER UTILITY DISTRIBUTION | closeout | Contract Closeout Submittals — Test Results. |  | CN-21P., CN-66. | draft |  |  |  |  | 0
rc23-349 | 33 13 00 | DISINFECTION OF WATER UTILITY DISTRIBUTION | closeout | Test Results. | Hach Chemical Co. | High range test kit for chlorine residual, DPD chlorine residual test kit, CN-21P., CN-66. | draft |  |  |  |  | 0
rc23-350 | 33 20 01 | SUBMERSIBLE WELL PUMP | manuals | Contract Closeout Submittals — Operation and Maintenance Data: Deliver 2 copies, covering the installed products, to the Director’s Representative. |  |  | draft |  |  |  |  | 0
rc23-351 | 33 20 01 | SUBMERSIBLE WELL PUMP | product_data | Product Data: Catalog sheets, specifications and installation instructions for each size pump. |  |  | draft |  |  |  |  | 0
rc23-352 | 33 20 01 | SUBMERSIBLE WELL PUMP | test_reports | Quality Control Submittals — Test Reports: Submit performance curves for each pump, showing capacity in gallons per minute, brake horsepower and efficiency from free delivery to shut-off head. Curves shall be based on factory tests by the manufacturer, in accordance with procedures recommended by the Hydraulic Institute. |  |  | draft |  |  |  |  | 0
rc23-318 | 33 31 04 | PLASTIC DRAINAGE PIPE (SANITARY) | product_data | Submittals Package: Submit the product data, samples, and quality control submittals specified below at the same time as a package. |  |  | draft |  |  |  |  | 0
rc23-334 | 33 31 04 | PLASTIC DRAINAGE PIPE (SANITARY) | product_data | Manufacturer’s specifications with all pertinent information regarding dimensions, fittings and installation instructions. | PVC Sewer Pipe and Fittings | PVC Sewer Pipe, Fittings | draft |  |  |  |  | 0
rc23-353 | 33 39 13 | MANHOLES AND DRAINAGE STRUCTURES WITH FRAMES AND COVERS | certificates | Environmental Product Declaration (EPD) from the manufacturer for concrete, if available. | Concrete Sealants, Inc, Neenah Foundry Company, Syracuse Castings, East Jordan Iron Works, Neenah, East Jordan Iron, A-Lok Products, Inc, Chardon Rubber Company, NPC, Inc, Thunderline Link-Seal, Inc |  | draft |  |  |  |  | 0
rc23-354 | 33 39 13 | MANHOLES AND DRAINAGE STRUCTURES WITH FRAMES AND COVERS | product_data | Manufacturer’s catalog cuts, specifications, and installation instructions. | Concrete Sealants, Inc, Neenah Foundry Company, Syracuse Castings, East Jordan Iron Works, Neenah, East Jordan Iron, A-Lok Products, Inc, Chardon Rubber Company, NPC, Inc, Thunderline Link-Seal, Inc |  | draft |  |  |  |  | 0
rc23-355 | 33 39 13 | MANHOLES AND DRAINAGE STRUCTURES WITH FRAMES AND COVERS | shop_drawings | Fabrication details and connections to adjacent Work. | Concrete Sealants, Inc, Neenah Foundry Company, Syracuse Castings, East Jordan Iron Works, Neenah, East Jordan Iron, A-Lok Products, Inc, Chardon Rubber Company, NPC, Inc, Thunderline Link-Seal, Inc |  | draft |  |  |  |  | 0
rc23-356 | 46 07 00 | PACKAGED WASTEWATER TREATMENT EQUIPMENT | closeout | Operation, Maintenance Data, and Parts Lists: Deliver 2 copies to the Director’s Representative. | Xerxes Corporation, which is located at: 7901, Underwriters Laboratories, AquaPoint is an acceptable means of providing |  | draft |  |  |  |  | 0
rc23-357 | 46 07 00 | PACKAGED WASTEWATER TREATMENT EQUIPMENT | other | Submittals shall include all equipment and components, catalogue cuts, wiring diagrams, control schematics and all pertinent installation, operation, and. | Xerxes Corporation, which is located at: 7901, Underwriters Laboratories, AquaPoint is an acceptable means of providing |  | draft |  |  |  |  | 0
rc23-358 | 46 07 00 | PACKAGED WASTEWATER TREATMENT EQUIPMENT | product_data | Manufacturer's data sheets on each product to be used, including preparation instructions, storage and handling requirements, installation manual and operating guidelines. | AQUAPOINT, Xerxes Corporation, which is located at: 7901, Underwriters Laboratories, AquaPoint is an acceptable means of providing |  | draft |  |  |  |  | 0
rc23-359 | 46 07 00 | PACKAGED WASTEWATER TREATMENT EQUIPMENT | shop_drawings | Detailed shop drawings of each tank complete with all accessories, detailed shipping, handling, and installation instructions. | AQUAPOINT, Xerxes Corporation, which is located at: 7901, Underwriters Laboratories, AquaPoint is an acceptable means of providing |  | draft |  |  |  |  | 0