## Submittal Checklist
Spec-to-Submittal Checklist
From SubPro . sub-pro-ai.com . Submittal automation for construction teams
1. Before you start
☐ | Collect the full spec book, all addenda, and the current drawing set.
☐ | Confirm project name, number, and the approved handoff location.
☐ | Confirm data-handling requirements (NDA or security process) if needed.
2. Read each specification section
☐ | Open each CSI section and find its submittals article (usually Part 1).
☐ | List every required item: product data, shop drawings, samples, test reports, certifications.
☐ | Note the submittal type and the responsible party for each item.
☐ | Record the source page number for every requirement.
3. Build the submittal log
☐ | Create one row per required submittal.
☐ | Capture CSI section, item description, type, responsible party, and source page.
☐ | Add review status (draft, needs review, ready) and a due date.
☐ | Flag rows that need a decision (substitutions, owner selections).
4. Assemble the packages
☐ | Gather product data and safety data sheets for each specified product.
☐ | Collect shop drawings and samples where the section requires them.
☐ | Build a package cover identifying project, section, and item.
☐ | Mark packages that are missing evidence instead of leaving gaps hidden.
5. Review before handoff
☐ | Check each row against its source page to confirm the requirement is real.
☐ | Resolve flagged decisions and substitutions with the responsible party.
☐ | Confirm nothing was missed by scanning every section once more.
☐ | Verify responsible parties and due dates are assigned.
6. Hand off clean
☐ | Export the submittal log and schedule as editable XLSX.
☐ | Export the PDF packages with transmittal covers.
☐ | Deliver to the approved project location and keep an audit record.
☐ | Load the source-backed set into your tracking and approval workflow.
Tip: SubPro can draft steps 2 and 3 automatically from the spec book, so your team reviews rows instead of typing them. See sub-pro-ai.com/how-subpro-works.