## Submittal Log
SUBMITTAL LOG
|  | Project: | [Project name] |  | Project No.: | [Number] | General Contractor: | [GC]
|  | Architect: | [A/E] |  | Log updated: |  | Owner: | [Owner]
Submit By, Review Due, Days in Review and Days Overdue calculate themselves from the dates you enter. Review period and buffer live on the Lists sheet.
Submittal # | Rev | Spec Section | Spec Title | Spec Para. | Type | Description | Manufacturer | Product / Model | Responsible Party | Ball in Court | Long-Lead | Lead Time (days) | Required On Site | Submit By | Date Sent | Review Due | Date Returned | Days in Review | Review Action | Status | Days Overdue | Package File | Notes
EX-001 | 0 | 03 30 00 | Cast-in-Place Concrete | 1.04.A | Product Data | Concrete mix designs with strength, slump, and admixture data (example, replace) | Local ready-mix | Mix 4000-A | Concrete sub | Closed | N | 14 | 2026-08-16 |  | 2026-07-21 |  | 2026-07-30 |  | No Exceptions Taken | Approved |  |  | Released to batch plant
EX-002 | 1 | 03 20 00 | Concrete Reinforcing | 1.03.B | Shop Drawings | Reinforcing steel placing drawings, slab on grade and footings (example, replace) |  |  | Concrete sub | Architect | N | 21 | 2026-09-17 |  | 2026-08-27 |  |  |  |  | Under Review |  |  | Revision 1 after bar schedule comments
EX-003 | 0 | 07 92 00 | Joint Sealants | 1.05.C | Samples | Sealant product data and color samples for exposed joints (example, replace) | Sika, Tremco | Sikaflex 1a | Finishes sub | Subcontractor | N | 10 | 2026-10-15 |  | 2026-08-06 |  | 2026-08-20 |  | Revise and Resubmit | Revise and Resubmit |  |  | Color range did not match finish schedule
EX-004 | 0 | 08 71 00 | Door Hardware | 1.04.D | Shop Drawings | Door hardware schedule and keying meeting minutes (example, replace) | Hager, Von Duprin | BB1279, 98 series | Supplier | Supplier | Y | 60 | 2026-11-19 | [6 empty] | Draft |  |  | Keying meeting scheduled with owner
EX-005 | 0 | 26 24 13 | Switchboards | 1.03.A | Product Data | Switchboard product data, ratings, and dimensioned drawings (example, replace) | Square D, Eaton | QED-2 | Electrical sub | Engineer | Y | 120 | 2027-02-02 |  | 2026-09-02 |  |  |  |  | Submitted |  |  | Long-lead, release drives the electrical room date
EX-006 | 0 | 07 54 23 | TPO Roofing | 1.06.B | Warranty | Sample manufacturer's 20-year warranty and installer certification (example, replace) | Carlisle | Sure-Weld 60 mil | Roofing sub | General Contractor | N | 30 | 2026-08-31 | [6 empty] | Pending Submission |  |  | Warranty start ties to substantial completion
Formulas:
Days in Review = IF([Date Sent]="","",IF([Date Returned]="",TODAY()-[Date Sent],[Date Returned]-[Date Sent]))
Days Overdue = IF(OR([Status]="Approved",[Status]="Approved as Noted",[Status]="Closed"),"",IF([Date Sent]="",IF(AND([Submit By]<>"",TODAY()>[Submit By]),TODAY()-[Submit By],""),IF([Date Returned]="",IF(TODAY()>[Review Due],TODAY()-[Review Due],""),"")))

## Dashboard
DASHBOARD
Counts update from the Submittal Log as you work. Nothing here is typed.
Total submittals | Open | Awaiting review
Overdue | Long-lead still open | Approved share
Avg. days in review (returned)
By status | By review action | Ball in court
Draft | No Exceptions Taken | Subcontractor
Pending Submission | Approved as Noted | Supplier
Submitted | Revise and Resubmit | General Contractor
Under Review | Rejected | Architect
Revise and Resubmit | Received for Record | Engineer
Approved as Noted |  | Owner
Approved |  | Closed
Rejected
Closed
Total
By division
01 General Requirements
02 Existing Conditions
03 Concrete
04 Masonry
05 Metals
06 Wood, Plastics, and Composites
07 Thermal and Moisture Protection
08 Openings
09 Finishes
10 Specialties
11 Equipment
12 Furnishings
13 Special Construction
14 Conveying Equipment
21 Fire Suppression
22 Plumbing
23 Heating, Ventilating, and Air Conditioning
25 Integrated Automation
26 Electrical
27 Communications
28 Electronic Safety and Security
31 Earthwork
32 Exterior Improvements
33 Utilities
Second column: rows. Third: overdue.

## Schedule
SUBMITTAL SCHEDULE
A dated view of the log, sorted by filtering. Days to Submit-By counts down from today; negative means late.
Submittal # | Spec Section | Description | Responsible Party | Long-Lead | Lead Time | Required On Site | Submit By | Days to Submit-By | Date Sent | Review Due | Status

## Transmittals
TRANSMITTAL LOG
One row per transmittal sent. The Submittals Enclosed column ties it back to the log.
Transmittal # | Date | To | Attention | From | Submittals Enclosed | Purpose | Method | Returned | Notes
T-001 | 2026-07-21 | [Architect firm] | Project architect | [GC] project engineer | EX-001 | For Review | Portal | 2026-07-30 | Example, replace
T-002 | 2026-08-06 | [Architect firm] | Project architect | [GC] project engineer | EX-003 | For Review | Email | 2026-08-20 | Example, replace
T-003 | 2026-08-27 | [Architect firm] | Project architect | [GC] project engineer | EX-002 (Rev 1) | Resubmittal | Portal |  | Example, replace

## Read Me
Submittal Log Pro, Burgundy edition. How to use it.
1. Put the project name, number, GC and architect in row 2 of the Submittal Log.
2. One row per required submittal. Number them under your project (TW 0024-001, 002...) and never reuse a number.
3. Type the spec section as the manual prints it, with spaces (08 71 00). The Dashboard counts divisions by those first two digits.
4. Enter Lead Time and Required On Site. Submit By calculates itself: required on site, less lead time, less the review period, less the buffer.
5. Enter Date Sent. Review Due and Days in Review calculate. Enter Date Returned and the Review Action when it comes back.
6. Days Overdue turns red on its own: before sending, against Submit By; after sending, against Review Due.
7. Six grey example rows show the shape. Delete them before you start.
8. Review period and buffer are two cells on the Lists sheet. Change them once and every date moves.
9. Add your own responsible parties on the Lists sheet; the dropdown reads them.
10. The Schedule sheet is the same rows by date. Filter it by Days to Submit-By to see what is late.
11. The Transmittals sheet records what went out and when. Tie each one back by submittal number.
Status values, colored on the log
Draft | Row identified, submittal not yet assembled
Pending Submission | Assembled, waiting to go out
Submitted | Sent to the reviewer, clock running
Under Review | With the reviewer now
Revise and Resubmit | Returned, resubmittal required
Approved as Noted | Returned with corrections, no resubmittal
Approved | Returned accepted, release for fabrication
Rejected | Returned rejected, new submittal required
Closed | Complete, nothing further owed
Review actions, as the stamp usually reads
No Exceptions Taken | Released as presented. Order it.
Approved as Noted | Released with the marked corrections. No resubmittal unless the stamp asks.
Revise and Resubmit | Correct and send again. Nothing released.
Rejected | Refused. A new submittal, not a revision.
Received for Record | Informational submittal, logged, no decision made.
Submittal types
Product Data | Manufacturer data sheets and technical data
Shop Drawings | Fabrication and installation drawings
Samples | Physical samples and color selections
Mock-up | Full-size or partial assembly built for review
Certificates | Certifications, affidavits, compliance letters
Test Reports | Lab and field test results
Qualification Data | Installer, fabricator or manufacturer qualifications
Design Data | Calculations and delegated design
Coordination Drawings | Multi-trade overlays
Warranty | Sample and executed warranties
O&M Manual | Operation and maintenance manuals
Closeout | Record documents and closeout items
Schedule | Schedules the manual requires as submittals
Sustainability | LEED and product declaration documents
Other | Anything else the manual demands
Template by SubPro, free to use on real projects. sub-pro-ai.com/submittal-log-template

## Lists
Settings |  | Types | Statuses | Review Actions | Ball in Court | Responsible Parties (edit) | Yes / No | Transmittal Purpose
Review period (working days the design team gets) | 14 | Product Data | Draft | No Exceptions Taken | Subcontractor | General Contractor | Y | For Review
Buffer (days of slack before the submit-by date) | 7 | Shop Drawings | Pending Submission | Approved as Noted | Supplier | Concrete sub | N | For Record
|  | Samples | Submitted | Revise and Resubmit | General Contractor | Steel sub |  | Resubmittal
|  | Mock-up | Under Review | Rejected | Architect | Roofing sub |  | Closeout
|  | Certificates | Revise and Resubmit | Received for Record | Engineer | Glazing sub
|  | Test Reports | Approved as Noted |  | Owner | Drywall sub
|  | Qualification Data | Approved |  | Closed | Finishes sub
|  | Design Data | Rejected |  |  | Mechanical sub
|  | Coordination Drawings | Closed |  |  | Plumbing sub
|  | Warranty |  |  |  | Electrical sub
|  | O&M Manual |  |  |  | Fire protection sub
|  | Closeout |  |  |  | Sitework sub
|  | Schedule |  |  |  | Supplier
Sustainability
Other
Add your own parties under the Responsible Parties column; the log dropdown reads down to row 40.

## Fill This In For Me
Want this filled in from your spec book?
The SubPro Log Build returns this log drafted and numbered for your project,
every row citing its spec page.
Draft Build, or Reviewed Build with every row human-reviewed.
sub-pro-ai.com/build-my-log