## Submittal Log
Submittal No. | CSI Section | Section Title | Submittal Description | Submittal Type | Spec Reference | Responsible Party | Status | Date Required | Date Submitted | Date Returned | Review Result | Notes
001 | 03 30 00 | Cast-in-Place Concrete | Concrete mix designs with compressive strength, slump, and admixture data (example, replace) | PD | 2.3.A | Concrete sub | Draft
002 | 07 92 00 | Joint Sealants | Sealant product data and color samples for exposed joints (example, replace) | PD, SA | 2.1.B | Sealant sub | Draft
003 | 08 71 00 | Door Hardware | Hardware schedule and keying meeting minutes (example, replace) | SD | 2.5.A | GC | Draft

## Legend
Submittal Type
PD | Product data
SD | Shop drawings
SA | Samples
QC | Quality control / certificates
CO | Closeout / O&M
Status values
Draft | Row identified, submittal not yet assembled
Submitted | Sent to reviewer
Approved | Returned approved
Approved as noted | Returned with comments, resubmittal not required
Revise and resubmit | Returned, resubmittal required
Template by SubPro | sub-pro-ai.com, free to use on real projects